## Risk Register
RISK REGISTER
ID | Risk Name | Date Raised | Risk & Impact Description | Likelihood | Consequences | Overall | Proposed Mitigation | Owner | Target Date to Resolve | Status
1.2 | Level 4 Lockdown | 2021-09-24 | Covid 19 is a virus that spreads easily in the community and could cause a level 4 lockdown which means that restriccions of where the people can go are in place, this would disrupt the learning curve and possible delay the dates of some of the project milestones. | Possible | Major | High | Online communication is key for this scenario as it would allow constant contact with all the stakeholders. | Jorge Campero | 2021-09-24 | open
2.1 | Contact covid case | 2021-09-24 | Covid 19 is a virus that spreads easily in the community and it is likely that one could be a close contact of a covid case which would mean that a test must be performed and isolation should last at least 14 days. | Likely | Major | Extreme | Online communication is key for this scenario as it would allow constant contact with all the stakeholders. | Jorge Campero | 2021-09-24 | open
3.1 | Internet cut | 2021-09-24 | The internet could be off for an unexpected event or for high demand.If the internet is off, then I would not be able to access online resources which would make the project to be delayed. | Unlikely | Moderate | Moderate | Keep local resources that might help with the development of the project. | Jorge Campero | 2021-09-24 | open
4.1 | Volcanic eruption | 2021-09-24 | Auckland's closest volcano is Rangitoto which has not have an eruption since 550 years ago. A volcanic eruption would erase the city and put in danger the lifes of hundreds of thousands of people. | Rare | Catastrophic | High | Delay the project until it is safe to continue. | Jorge Campero | 2021-09-24 | open
5.1 | PC gets broken | 2021-09-24 | If my device gets broken I would have to get a new one to continue working on the project. | Unlikely | Minor | Low | Ask the Unitec staff if I can borrow a laptop while doing the project. | Jorge Campero | 2021-09-24 | open

## Issues Register
ISSUES REGISTER
ID | Date Raised | Project | Issue Title | Issue Description | Specific Deliverable/Milestone affected | Likelihood | Consequences | Overall Issue Rating | Proposed Resolution / Mitigating Action | Issue Owner | Target Date to Resolve | Progress Status / Commentary | Open / Closed

## Risk Matrix
Unitec RISK FRAMEWORK
Likelihood/Impact | Insignificant | Minor | Moderate | Major | Catastrophic
Almost Certain | Moderate | High | High | Extreme | Extreme
Likely | Moderate | Moderate | High | Extreme | Extreme
Possible | Low | Moderate | High | High | Extreme
Unlikely | Low | Low | Moderate | High | High
Rare | Low | Low | Moderate | Moderate | High

## Data (hidden)
Likelihood | Consequences
Almost Certain | Insignificant
Likely | Minor
Possible | Moderate
Unlikely | Major
Rare | Catastrophic